## Dashboard
Press Conference — Master Schedule (Template)
Event Snapshot
Event name | Press conference — Lancement du Hub de Modèles 2026
Date | 2026-01-20
Start time | 9:30
Venue / address | Casablanca Finance City — Conference Hall (Casablanca)
Livestream link | YouTube Live (lien à renseigner)
Primary spokesperson | Amina Benali — CEO
Press kit link | Dossier presse (lien à renseigner)
Owner | AJANA ZAKARIA
Progress & KPIs
Run-of-show items |  | Notes
Items done |  | Notes
% done (run-of-show) |  | Notes
Logistics tasks |  | Notes
Logistics overdue |  | Notes
Media confirmed |  | Notes
Press attending |  | Notes

## Lists (hidden)
Status | Planned | Confirmed | In progress | Done | Blocked
Priority | Low | Medium | High | Critical
RSVP | Invited | Confirmed | Declined | No response | Attended
YesNo | Yes | No
Risk | Low | Medium | High
QAApproval | Draft | Legal review | Approved
BudgetStatus | Planned | Quoted | Approved | Invoiced | Paid

## Run_of_Show
Run of Show (Minute-by-minute)
ID | Start | End | Duration (min) | Segment | Speaker | Objective | AV / Cues | Owner | Priority | Status | Notes
S01 |  |  | 20 | Final AV check & speaker rehearsal | AV Team + Speakers | Align sound, slides, stage flow | Mic check • slides test • lights | AJANA ZAKARIA | High | Confirmed | Doors remain closed
S02 |  |  | 20 | Media check-in & coffee | Press desk | Accreditation + badges | Sign-in table • badges • press kit | AJANA ZAKARIA | Critical | Planned | Press desk opens
S03 |  |  | 5 | Seating & holding slide | Ushers | Seat press / start on time | Holding slide on screen | AJANA ZAKARIA | High | Planned
S04 |  |  | 5 | Opening remarks | Moderator (Head of Comms) | Welcome + ground rules | Livestream ON • timer | AJANA ZAKARIA | Critical | Planned | Record start time
S05 |  |  | 8 | Housekeeping & agenda | Comms Director | Set context + agenda + key rules | Cue agenda slide | AJANA ZAKARIA | High | Planned
S06 |  |  | 12 | Key announcement | Amina Benali (CEO) | Deliver core message + numbers | Key announcement slide | AJANA ZAKARIA | Critical | Planned | Keep to script
S07 |  |  | 10 | Supporting statement | Youssef El Amrani (Partner) | Partner perspective + credibility | Partner logo slide | AJANA ZAKARIA | High | Planned
S08 |  |  | 8 | Demo / visual highlights | Nadia Kabbaj (CTO) | Show what is new + benefits | Short demo video | AJANA ZAKARIA | High | Planned | Video tested in S01
S09 |  |  | 2 | Photo moment | Photographer | Official photo | Backdrop ready • step forward | AJANA ZAKARIA | Medium | Planned
S10 |  |  | 25 | Q&A (moderated) | Moderator + Panel | Answer press questions | Roving mic • timekeeper | AJANA ZAKARIA | Critical | Planned | Park off-topic items
S11 |  |  | 5 | Closing statement | Amina Benali (CEO) | Close + next steps | Closing slide • thank you | AJANA ZAKARIA | High | Planned
S12 |  |  | 15 | 1:1 interviews — Block 1 | CEO + selected outlets | Deep-dive interviews | Interview corner A | AJANA ZAKARIA | High | Planned | Prepare 3 key soundbites
S13 |  |  | 15 | 1:1 interviews — Block 2 | Partner + selected outlets | Partner interviews | Interview corner B | AJANA ZAKARIA | Medium | Planned
S14 |  |  | 10 | Photo ops / B-roll | Media + AV | B-roll capture | Demo area open | AJANA ZAKARIA | Medium | Planned
S15 |  |  | 5 | Internal debrief (quick) | Core team | Capture learnings + actions | 15-min debrief slot reserved | AJANA ZAKARIA | High | Planned | Assign owners for follow-ups

## Speakers
Speakers & Stakeholders
Name | Title | Organization | Mobile | Email | Arrival time | On-stage slot | Bio received | Photo received | Talking points | Notes
Amina Benali | CEO | Lecoursgratuit.com | +212 6 00 00 00 01 | amina.benali@example.com | 9:00 | 10:28 | Yes | Yes | Yes | Primary spokesperson
Nadia Kabbaj | CTO | Lecoursgratuit.com | +212 6 00 00 00 02 | nadia.kabbaj@example.com | 9:00 | 10:50 | Yes | No | Yes | Bring demo backup on USB
Youssef El Amrani | Partner Lead | Partner Org | +212 6 00 00 00 03 | youssef.elamrani@example.com | 9:10 | 10:40 | No | No | Yes | Confirm last wording
Sara El Idrissi | Comms Director | Lecoursgratuit.com | +212 6 00 00 00 04 | sara.elidrissi@example.com | 9:00 | 10:20 | Yes | Yes | Yes | Moderator briefing
Omar Bennis | Event Producer | Freelance | +212 6 00 00 00 05 | omar.bennis@example.com | 8:45 | 9:30 | Yes | Yes | Yes | Run-of-show owner

## Media_RSVP
Media List & RSVP Tracking
Outlet | Contact name | Role | Email | Phone | RSVP status | Accreditation | Dietary | Arrival time | Questions pre-submitted | Follow-up needed | Notes
2M | Rania O. | Journalist | rania@example.com | +212 6 10 00 00 01 | Confirmed | Yes |  | 9:50 | No | No | Camera position request
Medi1TV | Hicham A. | Reporter | hicham@example.com | +212 6 10 00 00 02 | Confirmed | Yes | Vegetarian | 9:50 | No | No
Le Matin | Salma B. | Editor | salma@example.com | +212 6 10 00 00 03 | Invited | Yes |  | 9:55 | Yes | Yes | Asked about pricing
L'Economiste | Karim L. | Business | karim@example.com | +212 6 10 00 00 04 | No response | No |  |  | No | Yes | Follow-up call
TelQuel | Meryem S. | Journalist | meryem@example.com | +212 6 10 00 00 05 | Confirmed | Yes |  | 10:00 | No | No
MAP | Desk | Agency | desk@example.com | +212 6 10 00 00 06 | Confirmed | Yes |  | 9:45 | No | No | Need press release at end
AFP | Bureau | Agency | afp@example.com | +212 6 10 00 00 07 | Invited | No |  |  | No | Yes | Confirm accreditation policy
Reuters | Stringer | Agency | reuters@example.com | +212 6 10 00 00 08 | Declined | No |  |  | No | No | Remote interest only
Hespress | Yassine K. | Online | yassine@example.com | +212 6 10 00 00 09 | Confirmed | Yes |  | 9:55 | Yes | No
EcoActu | Nora H. | Online | nora@example.com | +212 6 10 00 00 10 | No response | No |  |  | No | Yes | Second email reminder

## Logistics
Logistics Checklist (with deadlines)
Category | Task | Owner | Due date | Due time | Priority | Status | Overdue? | Notes
Venue | Confirm room layout + seating plan | Omar Bennis | 2026-01-15 | 16:00 | High | In progress |  | Finalize aisle for roving mic
Venue | Badges printed + lanyards ready | Sara El Idrissi | 2026-01-19 | 12:00 | High | Planned
AV | Test livestream encoder + backup recording | AV Vendor | 2026-01-19 | 18:00 | Critical | Planned |  | Backup local recording enabled
AV | Prepare roving mic x2 + batteries | AV Vendor | 2026-01-20 | 9:00 | High | Planned
Branding | Backdrop installed (logo wall) | Printer/Vendor | 2026-01-20 | 8:45 | High | Planned
Press | Press release final (FR/EN) | Comms Team | 2026-01-18 | 14:00 | Critical | In progress |  | Legal review in progress
Press | Media reminder email (24h) | Comms Team | 2026-01-19 | 9:00 | High | Planned
Security | Guest list shared with venue security | Omar Bennis | 2026-01-19 | 15:00 | High | Planned
Hospitality | Coffee + water + light snacks | Venue Catering | 2026-01-20 | 9:15 | Medium | Planned
Digital | Press kit folder updated (photos, bios, release) | Comms Team | 2026-01-19 | 20:00 | High | Planned

## Q_and_A
Q&A Preparation (Approved messaging)
Topic | Question | Recommended answer (short) | Proof points / data | Spokesperson | Risk | Approval | Last updated | Source link | Notes
Positionnement | Pourquoi lancer ce Hub en 2026 ? | Répondre à une demande massive de modèles prêts à l’emploi, avec une logique de qualité et de standardisation. | Trafic + téléchargements • retours utilisateurs • besoins formation | Amina Benali | Medium | Approved | 2026-01-17
Prix | Quel est le modèle économique ? | Freemium : un socle gratuit, et des packs premium pour les besoins avancés. | Segments (particuliers / pros) • packs • support | Amina Benali | Medium | Approved | 2026-01-17
Données | Collectez-vous des données personnelles ? | Nous collectons uniquement ce qui est nécessaire au service, avec des choix clairs pour l’utilisateur. | RGPD • minimisation • sécurité | Sara El Idrissi | High | Legal review | 2026-01-18 |  | Valider wording
Qualité | Comment garantissez-vous la fiabilité des modèles ? | Process : relecture, cas d’usage, versioning et retours utilisateurs. | Checklists • tests • audits internes | Nadia Kabbaj | Medium | Approved | 2026-01-18
Partenaires | Pourquoi ce partenariat ? | Pour accélérer la diffusion et renforcer l’impact : contenus, relais et terrain. | Réseau • expertise • distribution | Youssef El Amrani | Low | Approved | 2026-01-18
Roadmap | Quelles prochaines étapes ? | Nouveaux packs, dashboards, et versions sectorielles avec retours des utilisateurs. | Roadmap trimestrielle • retours • priorisation | Nadia Kabbaj | Medium | Draft | 2026-01-19
Support | Proposez-vous un support ? | Oui, un support pour les versions premium et une base d’aide structurée. | FAQ • tickets • SLA premium | Sara El Idrissi | Low | Draft | 2026-01-19
Impact | Quel impact pour les organisations ? | Gain de temps, standardisation documentaire, et meilleure traçabilité. | Exemples : réunions, RH, maintenance | Amina Benali | Low | Approved | 2026-01-17

## Budget
Budget & Vendor Tracker
Category | Vendor | Description | Qty | Unit cost | Line total | Status | Paid? | PO / Invoice # | Notes | Summary
Venue | CFC Venue | Room rental + basic setup | 1 | 4500 |  | Approved | No | PO-2026-001 |  | Total budget
AV | AV Vendor | Sound + 2 roving mics + projector | 1 | 6200 |  | Quoted | No | Q-AV-114 | Includes technician | Paid total
Branding | Print Shop | Backdrop (logo wall) + signage | 1 | 1800 |  | Approved | No | PO-2026-002 |  | Remaining
Hospitality | Catering | Coffee break (40 pax) | 40 | 6.5 |  | Planned | No |  | Adjust per RSVPs
Photo/Video | Photographer | Event coverage (2h) | 1 | 1500 |  | Approved | No | PO-2026-003
PR | PR Support | Press outreach + briefing | 1 | 2500 |  | Planned | No
Digital | Streaming | Livestream setup (platform) | 1 | 0 |  | Planned | Yes |  | In-house

## Timeline
Key Milestones & Prep Timeline
Workstream | Milestone | Owner | Date | Time | Status | Dependencies | Notes
Press | Save-the-date sent | Comms Team | 2026-01-06 | 10:00 | Done
Press | Media list validated | Sara El Idrissi | 2026-01-10 | 15:00 | Done
Content | Press release draft | Comms Team | 2026-01-13 | 12:00 | In progress | Legal feedback
Content | Q&A pack v1 | Comms Team | 2026-01-14 | 18:00 | In progress
Production | Backdrop + signage order | Omar Bennis | 2026-01-13 | 11:00 | Done
Production | Final run-of-show locked | AJANA ZAKARIA | 2026-01-18 | 17:00 | Planned | Speakers confirm timings
Production | Full technical rehearsal | AV Vendor | 2026-01-19 | 18:00 | Planned | Room access
Day-of | Crew call | Omar Bennis | 2026-01-20 | 8:45 | Planned
Day-of | Press desk opens | Press desk | 2026-01-20 | 9:50 | Planned

## Print_RunSheet
PRINT — Run Sheet
Event: |  |  | Venue:
Date:
Start | End | Segment | Speaker | AV / Cues | Owner | Priority | Status

## Reference
Reference (images provided)